## All Stories
Note: This sheet is optional.
XYZ project
No. | Feature Description
Iteration 1
Completed
76 | Identify additional fields that need to be added to X system
78 | Create page flow for X system
79 | Develop content for products
80 | Do options analysis for Voice system
86 | High Level System Architecture (DRAFT)
Iteration 2
Completed
73 | Identify LOE (hrs) by Feature by system. (As best we can in Iteration #2.) For all stories.
74 | Identify all resources needed & all external dependencies & delays. Covering all stories.
75 | Identify all releases and estimate all release dates. Includes all stories.
81 | Design algorithm for SRN/Access code - X system
84 | Options analysis for Y system access
94 | High Level System Architecture (for IT#2)
95 | "Planning" for next Iteration
Iteration 3
Selected
85 | Development environment setup
88 | Config Mgmt activities
95 | "Planning" for next Iteration
97 | MISC
100 | Revise estimates of remaining project at end of each iteration
T01 | Design X system to Z system Data Movement for New Data elements
T02 | Complete Data Requirements
T03 | Detailed Architecture Completion
T04 | Get commitment to telephony & middleware releases
T05 | Design doc for Voice Recognition status check
T06 | Collect Vendor 1 to Us infrastructure consensus
T07 | System A Interface Design
T08 | Create application look & feel
Iteration 4
After Iteration #5
Stories Removed (Various Reasons)

## Future Stories
This is the story backlog for future iterations.
No. | Code | Description | Required by | Bus Priority | Risk | Effort (Pts) | Iteration # | Status / Comments | Owner

## Contact-Details
For Iteration # 1
Group | Contact Name | Role | It.#1 hours | % |  | Rule of thumb |  | After Team Hours
| Bob |  | 40 | 100% |  | 28 |  | #VALUE!
| Darlene |  | 57.6 | 80% |  | 40.32 |  | #VALUE!
| Debbie |  | 0 | 0% |  | 0 |  | #VALUE!
| Doc |  | 28 | 35% |  | 19.6 |  | #VALUE!
| Kapil |  | 20 | 25% |  | 14 |  | 14
| Lee Patterson |  | 80 | 100% | * | 56 |  | #VALUE!
| Mark |  | 40 | 50% | * | 28 |  | #VALUE!
| Matt McLean |  | 0 | 0% | * | 0 |  | #VALUE!
| Pragati |  | 80 | 100% |  | 56 |  | #VALUE!
| Raji |  | 56 | 100% |  | 39.2 |  | #VALUE!
| Rama |  | 80 | 100% |  | 56 |  | #VALUE!
| Salai |  | 80 | 100% |  | 56 |  | #VALUE!
| Scott |  | 80 | 100% |  | 56 |  | #VALUE!
| Sharan |  | 29.6 | 37% |  | 20.72 |  | #VALUE!
| Srini |  | 4 | 5% |  | 2.8 |  | #VALUE!
| Vivek |  | 80 | 100% |  | 56 |  | #VALUE!
|  |  | 755.2 |  | hours | #VALUE! | Team
[5 empty] | 528.64 |  | we should sign up for this
|  |  | 0 |  |  |  | per R.o.Thumb

## Iteration Backlog - I#19
S.No | Story Group | Story Description | Story Priority | Lead | Task | Task Num | Hours | Orig Hrs | Performer | Category | Status | Comments
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Implement / Unit Test B System First Time | 352.1 | 2 | 2 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Implement / Unit Test Mail Second Time (+) | 352.2 | 2 | 2 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Implement / Unit Test C System Second Time | 352.3 | 2 | 2 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Implement / Unit Test Internet Second Time | 352.4 | 2 | 2 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Job Flow Testing for Infile Process | 352.5 | 4 | 4 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | OUT file Implement / Unit Test | 352.6 | 4 | 4 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | OUT file Job Flow Testing | 352.7 | 2 | 2 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | D.B. Support for IN/OUT | 352.8 | 4 | 4 | Mark | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Testcase design. IN / OUT file - Internet | 352.9 | 8 | 8 | Raji | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Testcase design. IN / OUT file - Mail | 352.1 | 8 | 8 | Raji | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Testcase design. IN / OUT file - Phone | 353.11 | 8 | 8 | Raji | Original
352 |  | IN/OUT Design & Build for It#19 |  | Mark | Bogey - testcase discussions & review | 352.13 | 2 | 2 | Raji, Pragati | Original
355 |  | DDE Documents [Prod Support Guide, D System Technical Document] |  | Sharan | Update Prod Support Guide | 355.1 | 8 | 8 | Sharan | Original
355 |  | DDE Documents [Prod Support Guide, D System Technical Document] |  | Sharan | Update DDE D System Technical Design document of new requirements & updating database changes in docs | 355.2 | 4 | 4 | Sharan | Original
356 |  | Teradata ZD & ZT containers |  | Kapil | Create Teradata Objects on ZDDOG and ZTDOG containers on ONEDEV | 356.1 | 10 | 10 | Kapil | Original
356 |  | Teradata ZD & ZT containers |  | Kapil | DB Changes validation & verification | 356.2 | 4 | 4 | Kapil | Original
356 |  | Teradata ZD & ZT containers |  | Kapil | Test containers | 356.3 | 2 | 2 | Srini | Original
357 |  | Doc Pop |  | Lee | Doc Pop Strategy | 357.1 | 4 | 4 | Lee, Scott | Original
357 |  | Doc Pop |  | Lee | Doc Pop DB Mods | 357.2 | 8 | 8 | Lee | Original
357 |  | Doc Pop |  | Lee | Doc Pop: Create Class to populate doc pop | 357.3 | 8 | 8 | Rama | Original
357 |  | Doc Pop |  | Lee | Doc Pop: 50% documents mapping to DB; binding with Doc Pop rules | 357.4 | 36 | 36 | Rama | Original
357 |  | Doc Pop |  | Lee | Doc Pop: understanding DB mapping for doc pop | 357.5 | 4 | 4 | Rama, Lee | Original
357 |  | Doc Pop |  | Lee | Doc Pop: Final Mapping - Easy button docs | 357.6 | 6 | 6 | Bob | Original
357 |  | Doc Pop |  | Lee | Doc Pop: Final Mapping - Complex docs | 357.7 | 6 | 6 | Bob | Original
358 |  | Marketing One Interface |  | Lee | E System DB Support | 358.1 | 4 | 4 | Lee | Original
358 |  | Marketing One Interface |  | Lee | E System Interface: New requirement coding | 358.2 | 4 | 4 | Sharan | Original
358 |  | Marketing One Interface |  | Lee | E System Interface: Unit testing | 358.3 | 4 | 4 | Sharan | Original
358 |  | Marketing One Interface |  | Lee | D System migration to QA | 358.4 | 2 | 2 | Sharan | Original
358 |  | Marketing One Interface |  | Lee | E System - Test | 358.5 | 10 | 10 | Pragati | Original
359 |  | Last Iteration Tweaks |  | Lee | Product Description: Intro Purch APR | 359.1 | 1 | 1 | Vivek | Original
359 |  | Last Iteration Tweaks |  | Lee | Tweaks | 359.2 | 1 | 1 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | DB Support for Interview | 360.1 | 8 | 8 | Lee | Original
360 |  | Interview screens 1-11 |  | Lee | Unit testing | 360.2 | 6 | 6 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | Bug fixing | 360.3 | 16 | 16 | Salai, Vivek | Original
360 |  | Interview screens 1-11 |  | Lee | Develop user controls | 360.4 | 8 | 8 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | XYZ Manager Design | 360.5 | 6 | 6 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | XYZ Manager Implement | 360.6 | 6 | 6 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | XYZ 5 | 360.7 | 8 | 8 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | XYZ 6 | 360.8 | 8 | 8 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | XYZ 7 | 360.9 | 6 | 6 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | XYZ 8 | 360.1 | 6 | 6 | Salai | Original
360 |  | Interview screens 1-11 |  | Lee | Build & labeling | 360.11 | 4 | 4 | Salai, Vivek | Original
360 |  | Interview screens 1-11 |  | Lee | App flow review / refactor | 360.12 | 1 | 1 | Scott, Salai, Vivek | Original | Done
360 |  | Interview screens 1-11 |  | Lee | Controls validation review | 360.13 | 1 | 1 | Scott, Salai, Vivek | Original | Done
360 |  | Interview screens 1-11 |  | Lee | Review retrieval & update method for app data | 360.14 | 1 | 1 | Scott, Salai, Vivek | Original
360 |  | Interview screens 1-11 |  | Lee | Review non-CDE & HC rules | 360.15 | 1 | 1 | Scott, Lee, Darlene | Original
360 |  | Interview screens 1-11 |  | Lee | Misc coord & facilitation | 360.16 | 36 | 36 | Scott | Original
360 |  | Interview screens 1-11 |  | Lee | Review docs data model | 360.17 | 1 | 1 | Scott, Lee | Original
360 |  | Interview screens 1-11 |  | Lee | XYZ Summary Mgmt | 360.18 | 8 | 8 | Scott | Original
360 |  | Interview screens 1-11 |  | Lee | Build, review, bugs | 360.19 | 8 | 8 | Scott | Original
360 |  | Interview screens 1-11 |  | Lee | Docs Assoc Engine | 360.2 | 8 | 8 | Scott | Original
360 |  | Interview screens 1-11 |  | Lee | State model: decline, withdraw, save | 360.21 | 8 | 8 | Scott | Original
360 |  | Interview screens 1-11 |  | Lee | Blue Bar | 360.22 | 2 | 2 | Vivek | Original
360 |  | Interview screens 1-11 |  | Lee | App tags & verification form | 360.32 | 2 | 2 | Vivek | Original
361 |  | MISC |  | Lee | Misc Coordination & Facilitation | 361.1 | 30 | 30 | Lee | Original
361 |  | MISC |  | Lee | Main system DB mapping / ID missing fields | 361.2 | 8 | 8 | Bob | Original
[6 empty] | TOTAL | 371 | 371
In Process
LATER
Done
DUP
REPLACED
Test Me

## I-19 Backlog Summary
| Sum of Hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri
S. No. | Story Description | 2006-08-14 | 2006-08-15 | 2006-08-16 | 2006-08-17 | 2006-08-18 | 2006-08-21 | 2006-08-22 | 2006-08-23 | 2006-08-24 | 2006-08-25
353 | Core Agile Practices for It#19 | 2006-08-14: 63
355 | DDE Documents [IPS Support Guide, M1 Technical Document] | 2006-08-14: 12
357 | Doc Pop | 2006-08-14: 72
352 | IN/OUT Design & Build for It#19 | 2006-08-14: 56
360 | Interview screens 1-11 | 2006-08-14: 235
359 | Last Iteration Tweaks | 2006-08-14: 2
358 | Marketing One Interface | 2006-08-14: 24
361 | MISC | 2006-08-14: 38
354 | Plan Management | 2006-08-14: 24
350 | PM & SDM Work for It#19 | 2006-08-14: 2
356 | Teradata ZD & ZT containers | 2006-08-14: 16
351 | Testing Plan for It#19 | 2006-08-14: 10
| TOTAL | 554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri
|  | 2006-08-14 | 2006-08-15 | 2006-08-16 | 2006-08-17 | 2006-08-18 | 2006-08-21 | 2006-08-22 | 2006-08-23 | 2006-08-24 | 2006-08-25
|  | 554 | [8 empty] | 0

## Pivot Table I-19
Sum of Hours
Story Description | Total
Core Agile Practices for It#19 | 63
DDE Documents [IPS Support Guide, M1 Technical Document] | 12
Doc Pop | 72
IN/OUT Design & Build for It#19 | 56
Interview screens 1-11 | 235
Last Iteration Tweaks | 2
Marketing One Interface | 24
MISC | 38
Plan Management | 24
PM & SDM Work for It#19 | 2
Teradata ZD & ZT containers | 16
Testing Plan for It#19 | 10
(blank)
Grand Total | 554

## Pivot by Status
Sum of Orig Hrs |  | Sum of Orig Hrs
Status | Total | Category | Total
Done | 32 | Original | 554
(blank) | 522 | (blank)
Grand Total | 554 | Grand Total | 554

## Pivot By Performer
TODAY
Sum of Hours
Performer | Total
Bob | 20
Bob, Darlene | 16
Darlene | 10
Darlene, Lee | 4
Kapil | 14
Lee | 50
Lee, Scott | 4
Mark | 22
Pragati | 44
Raji | 32
Raji, Pragati | 2
Rama | 44
Rama, Lee | 4
Salai | 55
Salai, Vivek | 20
Scott | 68
Scott, Lee | 1
Scott, Lee, Darlene | 1
Scott, Salai, Vivek | 3 | #VALUE! | Team
Sharan | 22
Srini | 2
Team | 57
Vivek | 55
Vivek, Lee | 2
Vivek, Salai, Darlene | 2
(blank)
Grand Total | 554

## Release Planning
S.No | Release date | Story code | Validation Date

## Issues
This sheet includes all obstacles (impediments), issues or action items
Item | Priority | Assigned
OBSTACLES
ACTION ITEMS