## Current Sprint Data Entry
| You can only edit white cells. All other cells are locked in order to protect their formulas. | [27 empty] | Scroll Back to the Left to find your Data.
| Sprint Backlog Data |  | (Spreadsheet Version 3) | [5 empty] | 2010-01-14 |  |  |  | 2010-01-15 |  |  |  | 2010-01-18 |  |  |  | 2010-01-19 |  |  |  | 2010-01-20
| Priority | Conversational Name | Card Type | Work Source | Original Estimate | Actual Investment | Complete? | % Reported | Total Achieved | Total Found | SPO Accept? | Balance | Total Achieved | Total Found | SPO Accept? | Balance | Total Achieved | Total Found | SPO Accept? | Balance | Total Achieved | Total Found | SPO Accept? | Balance | Total Achieved | Total Found | SPO Accept? | Balance
| 1 | User Story A | Planned | Production Support | 3 | 5 | Y | 100% |  |  |  | 3 | 1 |  |  | 2 | 1 |  |  | 1 | 1 | 2 |  | 2 | 2 |  | Accept | 0
| 2 | User Story B | Planned | Production Support | 8 | 8 | Y | 100% | 2 |  |  | 6 |  |  |  | 6 | 1 |  |  | 5 | 2 |  |  | 3 | 3 |  | Accept | 0
| 3 | User Story C | Planned | Production Support | 3 | 3 | Y | 100% |  |  |  | 3 | 1 |  |  | 2 | 1 |  |  | 1 |  |  |  | 1 | 1 |  | Accept | 0
| 4 | User Story D | Planned | Bug Fix | 3 | 5 | Y | 100% |  |  |  | 3 |  |  |  | 3 |  |  |  | 3 | 3 | 2 |  | 2 | 2 |  | Accept | 0
| 5 | User Story E | Planned | New Feature | 5 | 5 | Y | 100% | 1 |  |  | 4 |  |  |  | 4 | 2 |  |  | 2 | 2 |  | Accept | 0 |  |  |  | 0
| 6 | User Story F | Planned | Bug Fix | 3 | 3 | Y | 100% | 2 |  |  | 1 |  |  |  | 1 | 1 |  | Accept | 0 |  |  |  | 0 |  |  |  | 0
| 7 | User Story G | Planned | Production Support | 5 | 5 | Y | 100% |  |  |  | 5 |  |  |  | 5 |  |  |  | 5 | 3 |  |  | 2 | 2 |  | Accept | 0
| 8 | User Story H | Adopted | New Feature | 3 | 0 | N | 0% |  |  |  | 3 |  |  |  | 3 |  |  |  | 3 |  |  |  | 3 |  |  | Reject | 3
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
ScrollBack Up to Find Your Data
.pleh rof moc.liamg@murcS.lacitcarP ta ttocS tcatnoc nac uoY .9002 ,21 hcraM no yenwoD ttocS yb detaerc saw tnetnoc sti fo lla dna koobkrow sihT

## Trend Data Entry
| Sprint Data |  |  | Type the values from the red cells into the row for the current Sprint | [8 empty] | <<<PLEASE READ CAREFULLY>>>
|  |  |  | 33 | 30 | 3 | 4 | 4 | 34 | 82.5% | 86.67% | #REF! | To enter data for a new Sprint, simply enter the Team Size for the current Sprint in the first blank row. The date and number of the Sprint will automatically populate, and caution indicators will appear until you have entered values for Commit, Velocity, Adopted, Found and Capcity for that Sprint. Also, note that this form does contain a frozen pane (rows 1-4). If you suddenly find data missing, refer to Excel's row numbers and be sure they are contiguous; otherwise, scroll to the top.
Version 3
| Sprint # | Ending Date | Team Size | Commit | Velocity | Adopted | Found | Estimate Delta | Capacity | Accuracy of Commit | Accuracy of Estimation | Accuracy of Focus | Sprint Notes
0 | 2009-10-14 | 2009-10-14 | 6 | 5 | 5 | 6 | 8 | 0 | 45 | 26.32% | 26% | 11.11% | Sprint 62.2, Teams merged, cards got blocked, devs working on work not committed
0 | 2009-10-21 | 2009-10-21 | 6 | 7 | 7 | 0 | 10 | 2 | 20 | 41.18% | 41% | 71.11% | Sprint 63.1
0 | 2009-10-28 | 2009-10-28 | 5 | 20 | 15 | 0 | 12 | 10 | 25 | 46.88% | 74% | 77.78% | Sprint 63.2, Long Weekend, Out of sprint work ([COMPONENT])
0 | 2009-11-04 | 2009-11-04 | 6 | 22 | 13 | 5 | 12 | 9 | 35 | 33.33% | 73% | 51.11% | Sprint 64.1
0 | 2009-11-11 | 2009-11-11 | 7 | 25 | 18 | 0 | 10 | 5 | 33 | 51.43% | 89% | 66.67% | Sprint 64.2, IP List card external dependency, [COMPONENT]..vague requirements, SQL reporting….no access.
0 | 2009-11-18 | 2009-11-18 | 7 | 31 | 22 | 0 | 5 | 5 | 40 | 61.11% | 100% | 60% | Sprint 65.1, Failed [TEAM MEMBER] card as he didn’t want to deploy to Prod last minute
0 | 2009-11-25 | 2009-11-25 | 7 | 38 | 25 | 3 | 5 | 8 | 40 | 54.35% | 100% | 66.67% | Sprint 65.2, Many cards failed 'cuz the code was not checked in.
0 | 2009-12-02 | 2009-12-02 | 7 | 42 | 30 | 0 | 2 | 2 | 42 | 68.18% | 100% | 73.33% | Sprint 20090812, Original Sprint aborted and replanned due to critical issues with [FUNCTIONALITY]
0 | 2009-12-09 | 2009-12-09 | 6 | 33 | 18 | 5 | 2 | 7 | 38 | 45% | 100% | 55.56% | Sprint 20090819, [TEAM MEMBER] left in the middle
0 | 2009-12-16 | 2009-12-16 | 6 | 28 | 22 | 3 | 0 | 3 | 45 | 70.97% | 100% | 48.89% | Sprint 20090826, [EXTERNAL TEAM] not ready with video providers, DB queue implementation had some problems and failed
0 | 2009-12-23 | 2009-12-23 | 6 | 29 | 25 | 8 | 0 | 5 | 44 | 67.57% | 88% | 57.78% | Sprint 20091002, [TEAM MEMBER] joined in middle and fell sick
0 | 2009-12-30 | 2009-12-30 | 6 | 25 | 20 | 0 | 0 | 0 | 38 | 80% | 100% | 60% | Sprint 20090909
0 | 2010-01-06 | 2010-01-06 | 6 | 33 | 26 | 5 | 0 | 5 | 33 | 68.42% | 100% | 84.44% | Sprint 20090916, [TEAM MEMBER] was sick, [COMPONENT] not working due to config issues in stage boxes
0 | 2010-01-13 | 2010-01-13 | 6 | 35 | 29 | 8 | 0 | 6 | 43 | 67.44% | 94% | 68.89% | Sprint 20090923, [COMPONENT] became harder than first thought.
0 | 2010-01-20 | 2010-01-20 | 6 | 33 | 30 | 3 | 4 | 4 | 34 | 75% | 87% | 91.11%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
.pleh rof moc.liamg@murcS.lacitcarP ta ttocS tcatnoc nac uoY .9002 ,21 hcraM no yenwoD ttocS yb detaerc saw tnetnoc sti fo lla dna koobkrow sihT
Formulas:
Sprint # = IF(NOT([Ending Date]=""),[Ending Date],"")
Sprint # = IF(NOT([Team Size]=""),[Sprint #, row above]+7,"")
Ending Date = IF(AND(COUNT([Team Size],[Commit]:[Capacity])>0,NOT([Ending Date, row above]="")),[Ending Date, row above]+7,"")

## Charts
Workbook Version 3
Current Sprint
Velocity | 30
Work Capacity | 34
Focus Factor | 88.24%
% Found Work | 13.33%
% Adopted Work | 10%
Accuracy of…
…Commitment | 82.5%
…Estimation | 86.67%
Value Contribution | 500%
Ten Sprint Averages
Velocity | 24.7
Work Capacity | 39.7
Focus Factor | 62.22%
Found (Points) | 1.8
Adopted (Points) | 3.5
Accuracy of…
…Commitment | 89.3%
…Estimation | 86.24%
Value Contribution | 394%
Workbook Version 3
Workbook Version 3
Workbook Version 3
Workbook Version 3
Workbook Version 3

## Data (hidden)
Cards Reflected from CSDE | [9 empty] | Progress by Day | [14 empty] | Key Metrics
[10 empty] | Thurs |  |  | Fri |  |  | Mon |  |  | Tue |  |  | Wed |  |  | Current Sprint | Story Points | Original Commit | 30
Card Type | Original Estimates | Accepted | Found per Card | Planned Cards | Adopted Cards | Velocity per Card | Capacity per Card | Delivery | Estimate Delta | Achieved | Found | % | Achieved | Found | % | Achieved | Achieved | % | Achieved | Found | % | Achieved | Found | % |  |  | Total Commit | 33
Planned | 3 | Y | 2 | 3 | 0 | 3 | 5 | 5 | 2 | 0 | #N/A | 0% | 1 | #N/A | 3.03% | 1 | #N/A | 3.03% | 1 | 2 | 3.03% | 2 | #N/A | 6.061% |  |  | Total Adopted | 3
Planned | 8 | Y | 0 | 8 | 0 | 8 | 8 | 8 | 0 | 2 | #N/A | 6.061% | #N/A | #N/A | #N/A | 1 | #N/A | 3.03% | 2 | #N/A | 6.061% | 3 | #N/A | 9.091% |  |  | Total Capacity | 34
Planned | 3 | Y | 0 | 3 | 0 | 3 | 3 | 3 | 0 | 0 | #N/A | 0% | 1 | #N/A | 3.03% | 1 | #N/A | 3.03% | #N/A | #N/A | #N/A | 1 | #N/A | 3.03% |  |  | Total Found | 4
Planned | 3 | Y | 2 | 3 | 0 | 3 | 5 | 5 | 2 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3 | 2 | 9.091% | 2 | #N/A | 6.061% |  |  | Velocity | 30
Planned | 5 | Y | 0 | 5 | 0 | 5 | 5 | 5 | 0 | 1 | #N/A | 3.03% | #N/A | #N/A | #N/A | 2 | #N/A | 6.061% | 2 | #N/A | 6.061% | #N/A | #N/A | #N/A |  |  | Value Contribution | 500%
Planned | 3 | Y | 0 | 3 | 0 | 3 | 3 | 3 | 0 | 2 | #N/A | 6.061% | #N/A | #N/A | #N/A | 1 | #N/A | 3.03% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | Accuracy | Commit | 82.5% | Did you complete your originally committed work, to the best of your understanding, by the end of the Sprint? It may or may not have been accepted.
Planned | 5 | Y | 0 | 5 | 0 | 5 | 5 | 5 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3 | #N/A | 9.091% | 2 | #N/A | 6.061% |  |  | Estimation | 86.67% | How accurate were your original estimates from the Estimation/Planning Meeting?
Adopted | 3 | N | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | % | Found Work | 13.33%
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | Adopted Work | 10%
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Ten Sprint Averages | Metrics Trend | Velocity | 24.7
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | Work Capacity | 39.7
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | Found Work | 1.8
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | Adopted Work | 3.5
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | Accuracy Trend | Commit | 89.3% | Did you complete your originally committed work, to the best of your understanding, by the end of the Sprint? It may or may not have been accepted.
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  | Estimation | 86.24% | How accurate were your original estimates from the Estimation/Planning Meeting?
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #N/A | 0% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
0 | 0 |  | 0 | 0 | 0 | 0
Note on AC9: G. Scott Downey: Did you complete the originally committed work, to the best of your understanding, by the end of the Sprint?
Note on AC10: G. Scott Downey: Were your estimates accurate during the Planning or Estimation meeting?

## Unplanned (hidden)
| 2009-11-18 |  | 2009-11-25 |  |  | 2009-12-02 |  | 2009-12-09 |  | 2009-12-16 |  | 2009-12-23 |  | 2009-12-30 |  | 2010-01-06 |  | 2010-01-13 |  | 2010-01-20
| Adopted | Found | Adopted | Found | Adopted | Found | Adopted | Found | Adopted | Found | Adopted | Found | Adopted | Found | Adopted | Found | Adopted | Found | Adopted | Found
<18 | #N/A | 16.13% | #N/A | #N/A | #N/A | 4.762% | #N/A | #N/A | 10.71% | #N/A | #N/A | #N/A | #N/A | #N/A | 15.15% | #N/A | #N/A | #N/A | #N/A | #N/A
18<=x<=22 | #N/A | #N/A | 7.895% | 13.16% | #N/A | #N/A | 15.15% | 6.061% | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.091% | 12.12%
>22 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 27.59% | #N/A | #N/A | #N/A | #N/A | #N/A | 22.86% | #N/A | #N/A | #N/A
Reflected from Data Worksheet, Manually Flipped Above
| Sprint | Total | Adopted | Found | Max | Win | Loss
| 2009-11-18 | 16.13% | #N/A | 16.13% | 20% | 10% | #N/A
| 2009-11-25 | 21.05% | 7.895% | 13.16% | 20% | #N/A | 10%
| 2009-12-02 | 4.762% | #N/A | 4.762% | 20% | 10% | #N/A
| 2009-12-09 | 21.21% | 15.15% | 6.061% | 20% | #N/A | 10%
| 2009-12-16 | 10.71% | 10.71% | #N/A | 20% | 10% | #N/A
| 2009-12-23 | 27.59% | 27.59% | #N/A | 20% | #N/A | 10%
| 2009-12-30 | #N/A | #N/A | #N/A | 20% | 10% | #N/A
| 2010-01-06 | 15.15% | 15.15% | #N/A | 20% | 10% | #N/A
| 2010-01-13 | 22.86% | 22.86% | #N/A | 20% | #N/A | 10%
| 2010-01-20 | 21.21% | 9.091% | 12.12% | 20% | #N/A | 10%

## Card Progress (hidden)
Card |  |  |  |  | Progress |  |  |  |  | Toward Commit |  |  | Done
Number | Plot Shadow | Name | Estimate | Found | Thu | Fri | Mon | Tue | Wed | Reported | Estimated | Accepted | 90.91%
1 | 0% | User Story A...(Pri 1) | 3 | 2 | #N/A | 20% | 20% | 20% | 40% | 5 | 3 | 5
2 | 0% | User Story B...(Pri 2) | 8 | 0 | 25% | #N/A | 12.5% | 25% | 37.5% | 8 | 8 | 8
3 | 0% | User Story C...(Pri 3) | 3 | 0 | #N/A | 33.33% | 33.33% | #N/A | 33.33% | 3 | 3 | 3
4 | 0% | User Story D...(Pri 4) | 3 | 2 | #N/A | #N/A | #N/A | 60% | 40% | 5 | 3 | 5
5 | 0% | User Story E...(Pri 5) | 5 | 0 | 20% | #N/A | 40% | 40% | #N/A | 5 | 5 | 5
6 | 0% | User Story F...(Pri 6) | 3 | 0 | 66.67% | #N/A | 33.33% | #N/A | #N/A | 3 | 3 | 3
7 | 0% | User Story G...(Pri 7) | 5 | 0 | #N/A | #N/A | #N/A | 60% | 40% | 5 | 5 | 5
8 | 0% | User Story H...(Pri 8) | 3 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
#N/A | #N/A |  | 0 | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0
Note on B2: G. Scott Downey: Has to show as a percentage to make it plot correctly.

## Daily Focus (hidden)
Card Data |  |  | Thursday | [7 empty] | Friday | [7 empty] | Monday | [7 empty] | Tuesday | [7 empty] | Wednesday | [8 empty] | For Plotting | [5 empty] | For Calculations
|  |  | Status | [5 empty] | Invested |  | Status | [5 empty] | Invested |  | Status | [5 empty] | Invested |  | Status | [5 empty] | Invested |  | Status | [5 empty] | Invested |  |  | Thu | Fri | Mon | Tue | Wed |  | Thu | Fri | Mon | Tue | Wed
# | Est | Live? | Not Started |  | In Progress |  | Done |  | Now | All | Not Started |  | In Progress |  | Done |  | Now | All | Not Started |  | In Progress |  | Done |  | Now | All | Not Started |  | In Progress |  | Done |  | Now | All | Not Started |  | In Progress |  | Done |  | Now | All | NS | 17 | 11 | 11 | 3 | 3 | NS | 17 | 11 | 11 | 3 | 3
1 | 3 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 5 | IP | 16 | 22 | 19 | 22 | #N/A | IP | 16 | 22 | 19 | 22 | 0
[35 empty] | 0 | 0 | 0 | 0 | 1 | 8 | 3 | 8 | Done | #N/A | #N/A | 3 | 8 | 30 | % IP | 48.48% | 66.67% | 57.58% | 66.67% | 0%
2 | 8 | 1 | 0 | 0 | 1 | 8 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 8 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 8 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 3 | [6 empty] | Done | 0 | 0 | 3 | 8 | 30
3 | 3 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 5
4 | 3 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 5
5 | 5 | 1 | 0 | 0 | 1 | 5 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 5 | 2 | 5 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 3
6 | 3 | 1 | 0 | 0 | 1 | 3 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 5 | 2 | 5
7 | 5 | 1 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 0 | 0 | 3 | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0
8 | 3 | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
9 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
10 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
11 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
12 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
13 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
14 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
15 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
16 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
17 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
18 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
19 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
20 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
21 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
22 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
23 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
24 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
25 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
26 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
27 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
28 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
29 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
30 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
31 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
32 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
33 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
34 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY
35 | 0 | 0 | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | EMPTY | NS | 3 | IP | 0 | Done | 30
Totals: |  |  | NS | 17 | IP | 16 | Done | 0 |  |  | NS | 11 | IP | 22 | Done | 0 |  |  | NS | 11 | IP | 19 | Done | 3 |  |  | NS | 3 | IP | 22 | Done | 8

## Pie Charts (hidden)
| Work Type Distribution |  |  | Work Source Distribution
Card # | Planned | Adopted | Found | New Feature | Refactoring | Prod Support | Stage Bug | Research
1 | 3 | 0 | 2 | 0 | 0 | 3 | 0 | 0
2 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0
3 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0
4 | 3 | 0 | 2 | 0 | 0 | 0 | 3 | 0
5 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0
6 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0
7 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0
8 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals: | 81.08% | 8.108% | 10.81% | 24.24% | 0% | 57.58% | 18.18% | 0%

## Rolling (hidden)
10 Week Rolling Trend Data Reflected from TDE
Sprint Count | Sprint Name | Team Size | Commit | Velocity | Average Velocity | Estimate Delta | Capacity | Value Contribution | Adopted |  | Found |  | Total Adopt + Found Work
[9 empty] | Points | % | Points | %
9 | 2009-11-18 | 7 | 31 | 22 | #VALUE! | 5 | 40 | 340% | 0 | 0% | 5 | 16.13% | 16.13%
8 | 2009-11-25 | 7 | 38 | 25 | #VALUE! | 8 | 40 | 400% | 3 | 7.895% | 5 | 13.16% | 21.05%
7 | 2009-12-02 | 7 | 42 | 30 | #VALUE! | 2 | 42 | 500% | 0 | 0% | 2 | 4.762% | 4.762%
6 | 2009-12-09 | 6 | 33 | 18 | #VALUE! | 7 | 38 | 260% | 5 | 15.15% | 2 | 6.061% | 21.21%
5 | 2009-12-16 | 6 | 28 | 22 | 20.4375 | 3 | 45 | 340% | 3 | 10.71% | 0 | 0% | 10.71%
4 | 2009-12-23 | 6 | 29 | 25 | 15 | 5 | 44 | 400% | 8 | 27.59% | 0 | 0% | 27.59%
3 | 2009-12-30 | 6 | 25 | 20 | 13.5 | 0 | 38 | 300% | 0 | 0% | 0 | 0% | 0%
2 | 2010-01-06 | 6 | 33 | 26 | 20.5 | 5 | 33 | 420% | 5 | 15.15% | 0 | 0% | 15.15%
1 | 2010-01-13 | 6 | 35 | 29 | 21 | 6 | 43 | 480% | 8 | 22.86% | 0 | 0% | 22.86%
0 | 2010-01-20 | 6 | 33 | 30 | 24 | 4 | 34 | 500% | 3 | 9.091% | 4 | 12.12% | 21.21%

## Version (hidden)
Spreadsheet Version | 3
Date Published | 2009-12-11

## Brain (hidden)
Question | Answer
Did we win or lose this Sprint? | Win
Was our Velocity to Work Capacity ratio healthy (>=80%)? | Healthy
Was our Original Commit at least 80% of our Total Commit in the end? | Healthy
Was our total Unplanned Work in the save range of <=20% of the Total Commit? | Unhealthy
Was our amount of Found work by itself alright? | Healthy
Did we Adopt too much work? | Healthy
How was our Work In Progress percentage on…
Thursday? | Unhealthy
Friday? | Unhealthy
Monday? | Unhealthy
Tuesday? | Unhealthy
Wednesday? | Healthy
Did we vary outside the Cone of Uncertainty on…
Thursday?
Friday?
Monday?
Tuesday?
Wednesday?

## Accuracy (hidden)
Accuracy of…
X-Axis Labels | Rolling Counter | Sprint Name | Commit | Velocity | Adopted | Found | Commit | Delivery | Estimation | Focus | MAX | MIN
-9 | -9 | 2009-11-18 | 31 | 22 | 0 | 5 | 61.11% | #REF! | 100% | 60% | 85% | 75%
-8 | -8 | 2009-11-25 | 38 | 25 | 3 | 5 | 54.35% | #REF! | 100% | 66.67% | 85% | 75%
-7 | -7 | 2009-12-02 | 42 | 30 | 0 | 2 | 68.18% | #REF! | 100% | 73.33% | 85% | 75%
-6 | -6 | 2009-12-09 | 33 | 18 | 5 | 2 | 45% | #REF! | 100% | 55.56% | 85% | 75%
-5 | -5 | 2009-12-16 | 28 | 22 | 3 | 0 | 70.97% | #REF! | 100% | 48.89% | 85% | 75%
-4 | -4 | 2009-12-23 | 29 | 25 | 8 | 0 | 67.57% | #REF! | 88% | 57.78% | 85% | 75%
-3 | -3 | 2009-12-30 | 25 | 20 | 0 | 0 | 80% | #REF! | 100% | 60% | 85% | 75%
-2 | -2 | 2010-01-06 | 33 | 26 | 5 | 0 | 68.42% | #REF! | 100% | 84.44% | 85% | 75%
-1 | -1 | 2010-01-13 | 35 | 29 | 8 | 0 | 67.44% | #REF! | 94% | 68.89% | 85% | 75%
Now | 0 | 2010-01-20 | 33 | 30 | 3 | 4 | 75% | #REF! | 87% | 91.11% | 85% | 75%
Formulas:
Sprint Name = INDEX(Trend_Sprint_Number,COUNT(Trend_Sprint_Number)+[Rolling Counter])

## Formulas (hidden)
Accuracy | Commit | Velocity / SUM(Original Commit,Total Adopted,Total Found)
| Delivery | SUM(Total Effort on Accepted Cards) / SUM(Original Commit, Total Adopted, Total Found)
| Estimation | 1 - (SUM(Total Found, Total Original Estimates on Adopted) / Original Commit)
| Focus | 1 - ( (Work Capacity - Velocity) / MAX(Rolling Capacity) )

## Burndown (hidden)
| Thu |  | Fri |  | Mon |  | Tue |  | Wed
| Planned | Remaining | Found | Remaining | Found | Remaining | Found | Remaining | Found | Remaining
+20 | 36 | 32 | #N/A | 24 | #N/A | 16 | #N/A | 8 | #N/A | 0
Ideal | 30 | 26.6667 | #N/A | 20 | #N/A | 13.3333 | #N/A | 6.6667 | #N/A | 0
-20 | 24 | 21.3333 | #N/A | 16 | #N/A | 10.6667 | #N/A | 5.3333 | #N/A | 0
Actual | 30 | 28 | #N/A | 26 | #N/A | 20 | 24 | 13 | #N/A | 3
Act Mark | 30 | 28 | #N/A | 26 | #N/A | 20 | #N/A | 13 | #N/A | 3